## Sheet1
Date | Start/end times | Minutes | Description
2018-04-03 | 1:00 pm - 3:00 pm | 120 | Researched ideas for the project having to do with sleep. Things that can make sleep more efficient.
2018-04-04 | 4:30 pm - 5:30 pm | 60 | Found ideas for alarm clocks that would help people get up in the morning. Here is a link to some inventions I found: https://www.boredpanda.com/20-annoyingly-creative-alarm-clocks/
2018-04-06 | 12:20 pm - 1:00 pm | 40 | Searched for different LCD screens for myracecar alarm clock project.
2018-04-07 | 3:00 pm - 3:30 pm | 30 | Looked up how to configure RTC onto the LCD screen I found: https://www.itead.cc/nextion-nx4024t032.html
2018-04-09 | 12:00 pm - 2:30 pm | 150 | Ordered the parts I needed from amazon such as the DS3231 RTC, the Nextion 3.2 LCD screen, a speaker, and an amplifier for the speaker.
2018-04-11 | 5:00 pm - 7:00 pm | 120 | Researched ways to configure to HC05 bluetooth module without arduino. Also started creating a library for the RTC module.
2018-04-14 | 1:00 pm - 4:00 pm | 180 | Received my RTC module and LCD screen. Worked on how to control the LCD display.
2018-04-16 | 5:00 pm - 7:30 pm | 150 | Received my speaker from adafruit and watched videos and tutorials on how to use it with the amplifier.
2018-04-18 | 12:00 pm - 3:30 pm | 210 | Worked on the RTC module and making a clock with all the details.
2018-04-19 | 11:00 am - 2:00 pm | 120 | Downloaded Nextion Editor for the Nextion display and read tutorials on how to use it: https://www.itead.cc/wiki/Nextion_Editor_Quick_Start_Guide
2018-04-20 | 1:00 pm - 4:00 pm | 180 | Made my first display on the Nextion modeled after an alarm clock. Tried to use serial communication between Atmega and the Nextion display, but was unsuccessful.
2018-04-21 | 1:00 pm - 3:00 pm | 120 | Started working on using the DC motors for the base of my mobile alarm clock.
2018-04-23 | 1:30 pm - 4:00pm | 150 | Managed to receive data from the Nextion display, but could not send information to the display.
2018-04-24 | 4:00 pm - 7:30 pm | 210 | Started integrating the RTC module with the display. Could not send information to the display.
2018-04-25 | 6:00 pm - 10:00 pm | 240 | Made a working system with the RTC module and a simple LCD screen because I could not with the Nextion.
2018-04-26 | 12:00 pm - 5:00 pm | 300 | Tried to connected the RTC alarm clock with the DC motors via bluetooth
2018-04-26 | 7:00 pm - 9:00 pm | 180 | Tried to connected the RTC alarm clock with the DC motors via bluetooth
2018-04-28 | 4:00 pm - 7:30 pm | 210 | Attempted to connect the bluetooth modules via Arduino and then manipulate them using AVR.
2018-04-29 | 11:00 am - 5:00 pm | 360 | Created library for lcd module to test the workings of the alarm system with the RTC modue and the DC motors
2018-04-30 | 10:00 am - 4:00 pm | 360 | Worked on the bluetooth modules.
2018-05-01 | 11:00 am - 3:00 pm | 240 | Worked on connected the RTC to the Nextion display.
2018-05-01 | 5:00 pm - 10:00 pm | 300 | Configured Nextion libraries to format onto the Atmega 1284.
5/1/2018-5/2/2018 | 11:00 pm - 4:00 am | 300 | Started building a racecar model for my product as well as a case for the alarm clock display.
2018-05-02 | 2:00 pm - 6:00 pm | 240 | Worked on configuring speakers with the 3.7 D amplifier.
2018-05-02 | 11:00 pm - 7:00 am | 480 | Tried to get the Nextion display working and the bluetooth before the demo, but could not so used 2x16 and USART instead for temporary purpose. Created a working basic system of my racecar alarm clock.
2018-05-12 | 12:00 pm - 2:30 pm | 150 | Wrote code for the speaker and integrating it with the alarm.
2018-05-13 | 11:00 am - 3:00 pm | 180 | Connected the DC motors to the wheels and connected the two wheels for the back of the car.
2018-05-15 | 2:00 pm - 6:00 pm | 240 | Started measuring the dimensions of the breadboard and the components to start making wooden alarm box. Began cutting wood.
2018-05-17 | 10:00 am - 1:00 pm | 180 | Paired the bluetooth modules and integrated with system.
2018-05-19 | 9:00 am - 1:00 pm | 240 | Successfully transferred data between the bluetooth modules.
2018-05-20 | 9:00 am - 11:00 am | 120 | Added sensor to the racecar.
2018-05-26 | 9:00 am - 1:00 pm | 240 | Researched how to use PWM with DC Motors.
2018-05-31 | 10:00am - 1:00 pm | 180 | Figured out how to use PWM with a DC motor and control the speed.
2018-06-02 | 9:00 am - 10:am | 60 | Researched how to use PWM with two DC motors and change the speed separately.
2018-06-03 | 7:00 am - 12:00 pm | 300 | Figured out how to use PWM with two DC motors and control the speed of both.
2018-06-03 | 5:00 pm - 10:00 pm | 300 | Started putting box together and building 3rd wheel of car.
2018-06-04 | 1:00 pm - 5:00 pm | 240 | Built axel for 3rd wheel of car.
2018-06-04 | 6:00 pm - 9:00 pm | 180 | Transferred componets to small breadboard installed on body of car.
2018-06-05 | 10:00 am - 3:00 pm | 300 | Built wooden housing for car and made slots in alarm box for components.
2018-06-05 | 6:00 pm - 10:00 pm | 240 | Polished alarm clock and transferred alarm components to alarm box and smaller breadboard.
2018-06-06 | 9:00 am - 12:00 pm | 180 | Glued box together and started testing with car.
2018-06-06 | 3:00 pm - 9:30 pm | 390 | Debugging code, not functioning. Switched to old LCD.
2018-06-06 | 11:00 pm - 2:00 am | 180 | Finishing touches to project.
2018-06-06 | 5:00 am - 9:00 am | 240 | Finished design document and updated log.
| Total minutes | 9190